## aLIGO 42015
Risk Description | sub-System | Probability (%) | Cost to Fix (M$) | Time to Fix (m) | BNS Impact (% Range) | BBH Impact (% Range) | Total Severity
Gravity Gradient too high | SEI | 75 | 0.3 | 5 | 10 | 90
Thermal Distortion destabilizes ASC | AOS | 60 | 0.5 | 18 | 30 | 50
OMC PZT noise too high | LSC | 15 | 0.1 | 2 | 5 | 5
LSC Aux noise too high | LSC | 25 | 0.03 | 3 | 15 | 15
ASC feedback noise too high | ASC | 65 | 0.03 | 6 | 5 | 90
Beamtube Backscatter | SYS | 33 | 0.15 | 5 | 3 | 65
SRC Mode Healing -> Harming | SYS | 50 | 0.5 | 6 | 40 | 5
BS clipping -> contrast defect | COC | 90 | 0.35 | 6 | 33 | 3
ETM Charge fluctuations | SUS | 50 | 0.2 | 4 | 15 | 40
Parametric Instabilities | LSC | 70 | 0.2 | 4 | 40 | 5
Suspension crackle | SUS | 25 | 0.25 | 7 | 5 | 50
Coating thermal noise anomaly | COC | 20 | 0.75 | 8 | 30 | 3
OMC backscatter | LSC | 55 | 0.1 | 3 | 10 | 2
HAM6 Acoustics | SYS | 70 | 0.1 | 2 | 10 | 3
Residual Gas | SYS | 40 | 0.6 | 4 | 30 | 5
Bounce/Roll modes | SUS | 80 | 0.15 | 3 | 20 | 95
Violin Modes | SUS | 35 | 0.15 | 3 | 80 | 10
CDS/SEI breaks SUS fiber | SEI | 10 | 0.03 | 3 | 100 | 100